## Requirements
RqmtNo | Requirements | Story | Assigned To
-1 | Create GIT Project | create ageneral GIT project | VC
1 | Admin - User Account functionality | This is an admin functionality for the web app. This functionality is about creating different types of users and their associated properties. | JY
2 | Jobseeker - Search and View Job Posts | This functionality is about a jobseeker looking for job posts as per his requirement. | TS
3 | Jobseeker - upload /download/delete resume/s |  | MP
4 | Employer - Posting jobs |  | SK
6 | Employer - Search jobseekers |  | ZD
7 | Jobseeker - Add jobs as favorites after search |  | TS
8 | Employer - Add jobseekers as favorites before selecting an jobseeker for the interview |  | ZD
9 | JobSeeker - Job recommendations for the JS | This functionality is about recommending job posts to a jobseeker based on location, years of experience, and field | MouradH
10 | Communication - Jobseeker and Employer communicates. |  | MarlonH
11 | Jobseeker - Add employers as favorites. |  | MS
12 | Jobseeker - Apply for a job |  | SY
13 | Admin - Type of Jobs,Job Locations |  | JY
14 | Employer - Select applicants and move to the next step |  | AG
15 | Bulletin board - Publish news,tech articles etc.. |  | Sumit
| Sprint planning | Tasks | Subtasks | Assign
1 | Admin-User Account Functionality - Login functionality - User Authentication,Register new User ,Authorisation - based on the roles JS,E | Login Page with a link to Register Users | Web Page for Login and a link to Register as New User
Design and Create User table
Register new User Page
2 | Jobseeker - Search and View Job Posts,Jobseeker - Add jobs as favorites after search | View a job posts | Design and create tables for getting job posts information
Create queries for viewing job posts
Implement business logic in Java
Create a Web page for viewing posts
|  | Search for the job posts | Implement business logic in Java
Add new controls to the web page
|  | Add job posts to favorites | Create queries for favorites user posts
Implement business logic in Java
Add new components to the web page
Change behavior of favorite component on page if post was liked before
9 | JobSeeker - Job recommendations for the Jobseeker | JSP - create new page for displaying recommended job posts | Edit viewposts.jsp to display the recommended page link
create recommnded.jsp for dislpaying the job posts
|  | SQL - Query tables to get matches based on location / field / level of experience | add column for 'years of experience' in Users table and in Job_post table
add column for 'field' in jobseekers table